## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-19
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | make final adjustements to the funtionalities from reviews | Day 0: 4; Day 2: 2; Day 3: 2
2 | organize repo | Day 0: 2; Day 4: 1
3 | make improvements to the final report | Day 0: 4; Day 4: 1
4 | create unit tests | Day 0: 3; Day 3: 1
5 | make imporvements to the documents | Day 0: 4; Day 3: 1; Day 4: 1
6 | final meetings | 3 |  | 1 | 1 | 1 | 1
7 |  | Day 0: 0
8 |  | Day 0: 0
9 |  | Day 0: 0
10 |  | Day 0: 0
Completed Effort |  | 0 | 0 | 3 | 5 | 4 | 1 | 0 | 0
Remaining Effort |  | 20 | 20 | 17 | 12 | 8 | 7 | 7 | 7
Ideal Burndown |  | 20 | 18.6667 | 17.3333 | 16 | 14.6667 | 13.3333 | 12 | 10.6667