## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Setup the FreeCol repository. | bar: Day 0 to Day 1
2 | Study the existing source code. | Day 0: 3; Day 2: 1; Day 3: 1; Day 5: 1
3 | Extract exhaustive information. | 4 |  |  | 1 | 1 | 1 | 1
4 | Identify metrics. | Day 0: 0
5 | Design pattern identification. | Day 0: 0
6 | Pinpoint code smells. | Day 0: 0
7 | Compile reports (Metrics, GoF, Smells). | Day 0: 0
8 | Implement a round clock with 30s timer | Day 0: 0
9 | Enlarge graphic zoom | Day 0: 0
10 | Soldiers get a plus 1 movement unit when passing through sand | Day 0: 0
Completed Effort |  | 0 | 1 | 1 | 2 | 1 | 2 | 1 | 0
Remaining Effort |  | 8 | 7 | 6 | 4 | 3 | 1 | 0 | 0
Ideal Burndown |  | 8 | 7.4667 | 6.9333 | 6.4 | 5.8667 | 5.3333 | 4.8 | 4.2667