## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | make final adjustements to the funtionalities from reviews | 4 |  | 2 | 2
2 | organize repo | 2 |  |  |  | 1 | 1
3 | make improvements to the final report | 4 |  |  |  | 1 | 3
4 | create unit tests | 3 |  | 1 | 1 | 1 | 1
5 | make imporvements to the documents | 4 | 1 |  | 1 | 1 | 1
6 | final meetings | 3 |  | 1 | 1 | 1 | 1
7 |  | 0
8 |  | 0
9 |  | 0
10 |  | 0
Completed Effort |  | 0 | 1 | 4 | 5 | 5 | 7 | 0 | 0
Remaining Effort |  | 20 | 19 | 15 | 10 | 5 | -2 | -2 | -2
Ideal Burndown |  | 20 | 18.6667 | 17.3333 | 16 | 14.6667 | 13.3333 | 12 | 10.6667